## v0.1 (hidden)
PMS OPERATIONAL WORKFLOW
Phase | Step | Action | Responsibility | Document/Output
I. INITIATION | 1 | Identify clients due for PMS (1-year mark) via PMS Calendar (Summary) | Aftersales Engr | Excel Tracker
| 2 | Send PMS Cost Proposal to client. | Aftersales Engr | PMS Proposal
II. APPROVAL | 3 | Client Approval & 50% Downpayment. | Client | Proof of Payment
| 4 | Verify payment and confirm service schedule. | Aftersales Engr | Confirmation Email
III. EXECUTION | 5 | Issue Job Order (JO) to Contractor | Aftersales Engr | Job Order (JO)
| 6 | On-site Service: Cleaning, Retightening, & Thermal Scan. | Contractor | Technical Checklist
| 7 | Submit Site Report (w/ before and after photos). | Contractor | PMS Report
IV. CLOSING | 8 | Review and approve Contractor's report for quality. | Aftersales Engr | Approved Report
| 9 | Send Approved Report and Final Invoice (50%). | Aftersales Engr | Final Invoice
| 10 | Final Payment received and Contractor payout processed. | Aftersales Engr | Official Receipt
No schedule shall be locked in the calendar until the 50% Downpayment is confirmed by the finance/aftersales department.
The final 50% billing is sent simultaneously with the PMS Report.
The contract with the third-party contractor should mirror this; they should understand that their payout depends on the submission and approval of the report, not just the physical cleaning.

## v0.2
PMS OPERATIONAL WORKFLOW
Phase | Swimlane | Step | Sub-Status | Odoo - Nabeel | Odoo - Archelle | Fields | Action | TAT | Responsibility | System | Output | Remarks | Remarks
I. INITIATION | New Request | 1 |  | New Request |  |  | Identify clients due for PMS (1-year mark) via PMS Calendar (Summary) |  | Aftersales Engr | Google Drive | Google Sheets | Email Reminder: PMS Email Reminder 30March2026
| New Request | 2 | Pending Schedule | New Request |  |  | Send the reminder with PMS questionnaire link (https://www.solvivaenergy.com/customer-support/technical); Should be 30 days before anniversary - Target date of PMS (should be 10 days from the day you are filling out the form, Need to determine easy access (do we need ladder or scaffolding, and work permit requirements); Should automatically create Maintenance under the Project |  | Aftersales Engr | Customer Portal | Email | @archelle.natanauan@aboitizpower.com , can we check the inspection list so we can eliminate and work requirements: https://docs.google.com/document/d/1uIQSu5IDsInxQBA5VgJ5LJEIv7IQJHUZDL2RvST7PD8/edit?usp=drive_link
| New Request | 3 |  | Proposal Sent |  |  | Answer the questionnaire for PMS |  | Client | Website | Ticket
| New Request | 4 |  | Proposal Sent |  |  | Get the answer of the client |  | Aftersales Engr | Odoo | FAQs-based answer | Use the PMS module of Odoo
| New Request | 5 |  | Proposal Sent |  |  | Prepare proposal |  | Aftersales Engr | Odoo | Proposal | PMS Proposal (to client).docx
| New Request | 6 | Proposal: Sent, For Sending | Proposal Sent |  | Upload Contract | Send PMS Cost Proposal and Contract to client that will serve as a reminder 30 days before installation anniversary |  | Aftersales Engr | Odoo | Proposal | Any outside cost shall be billed separately
II. APPROVAL | In Progress | 7 |  | Proposal Sent |  |  | Send signed proposal to Solviva plus proof of payment as a reply to initial email |  | Aftersales Engr | Odoo | Signed proposal
| In Progress | 8 | Confirmed Schedule | Proposal Sent |  |  | Verify payment and confirm with Aftersales |  | Finance | Odoo | Bank Statement
| In Progress | 9 |  | Confirmed Schedule |  |  | Issue Job Order (JO) or Notice to Proceed to Contractor |  | Aftersales Engr | Odoo
| In Progress | 10 | Ready for Deployment | Confirmed Schedule |  | Upload NTP | Confirm the schedule and share work permit requirements, if any |  | Contractor | Google Drive | Google Sheets
| In Progress | 11 |  | Ready for Deployment |  |  | Send reminder (date, time, and duration) + expectation pre, during, and post PMS 3 days before the scheduled PMS |  | Aftersales Engr | Odoo | Confirmation of client | Can this be at least 1 week before?
| In Progress | 12 |  | Ready for Deployment |  |  | If there is a change in schedule, inform Contractor |  | Aftersales Engr | Viber / Google Drive | Confirmation of Contractor
| In Progress | 13 |  | Ready for Deployment |  |  | Send reminder (date, time, and duration) + expectation pre, during, and post a day before the scheduled PMS |  | Aftersales Engr | Odoo | Confirmation of client | Rescheduled date should be within the month
| In Progress | 14 |  | Ready for Deployment |  |  | If there is a change in schedule, inform Contractor |  | Aftersales Engr | Viber / Google Drive | Confirmation of Contractor
III. EXECUTION | In Progress | 15 | Maintenance Activity | Maintenance Activity |  | Upload Photos | Proceed with PMS and take photos before and after |  | Contractor | Viber | Must be together with the Client or with Client approval
| In Progress | 16 |  | Maintenance Activity |  |  | Communicate urgent concerns, if any |  | Contractor | Viber
| In Progress | 17 |  | Maintenance Activity |  |  | Address or escalate concerns |  | Aftersales Engr | Viber
| In Progress | 18 | System Valaidation | Maintenance Activity |  | Upload screenshot of Monitoring App | Submit Editable Site Report (w/ before and after photos). |  | Contractor | Google Drive | PMS report based on our template in Word file | PMS Report - Duplicate Only [Project Name - Date] (2).docx
| In Progress | 19 |  | Report Validation |  |  | Review Contractor's report for quality |  | Aftersales Engr | Google Drive | PMS report based on our template in Word file
| In Progress | 20 |  | Report Validation |  |  | Approve and sign Contractor's report for quality |  | Aftersales Engr | Google Drive | PMS Report PDF
| In Progress | 21 |  | Report Validation |  |  | Upload the signed Contractor's report |  | Aftersales Engr | Odoo | PMS Report PDF
| In Progress | 22 |  | Report Validation |  |  | Send invoice for outstanding balance of 50% and survey |  | Finance | Odoo | Invoice and Survey
| In Progress | 23 | Pending Report | Report Validation |  | Upload Proof Of Payment | Send proof of payment |  | Client | Email | Proof of payment
| Done | 24 |  | Report Validation |  | Upload Report | Send Approved Report |  | Aftersales Engr | Odoo | PMS Report PDF
IV. CLOSING | Done | 25 |  | Report Validation |  |  | Send signed Approved Report |  | Client | Odoo | Accomplished PMS Report PDF
| Done | 26 |  | Done |  |  | Send service invoice to Solviva |  | Contractor | Email | Service invoice
| Done | 27 |  | Done |  |  | Process payment to Contractor |  | Aftersales Engr | Optikus | With approved and verified Statement of Work Accomplishment
| Done | 28 | Completed | Done |  | Upload screenshot of Monitoring App | Monitor post-PMS |  | Aftersales Engr | Google Drive / Odoo | Google Sheet / Dashboard

## Comms Workflow
Steps 2 to 3
Trigger | a. 1-Year Installation Anniversary Detected [Day 0] b. Aftersales Engineer checks the PMS Calendar (Google Drive/Sheets) for clients approaching their 1-year mark. This is the trigger for the entire Step 2 sequence. c. Channels: Google Drive, Google Sheets
Step 1 — Initial Reminder | .
;.
DECISION: Did the client respond within 3 days? | YES — Proceed to schedule confirmation (Step 3 in main workflow). NO — Trigger Follow-Up #1 below.
Follow-Up #1 — Gentle Nudge | a. Follow-Up #1 — Gentle Nudge [Day 4] b. If no response after 3 days, Aftersales Engr sends a brief follow-up email and flag Sales Rep Channel/s: Email
DECISION: Did the client respond within 2 more days? | YES — Proceed to schedule confirmation. NO — Trigger Follow-Up #2 below.
Follow-Up #2 — Stronger Reminder | a. Follow-Up #2 — Stronger Reminder [Day 7] b. Aftersales Engr sends a firmer follow-up noting the upcoming anniversary and that unscheduled PMS may affect the service agreement. Attempt a phone call if email and Viber remain unanswered. Channel/s: Email
DECISION: Still no response after Day 7? | YES — Proceed to schedule confirmation. NO — Sales should coordinate with client for PMS scheduling
DECISION: Still no response after Day 10? | Include in next month's PMS reminder
Step 6
Trigger | CLIENT receives Proposal via Email through Odoo From: Aftersales Engr https://docs.google.com/document/d/1zrncD5M-Ky-O2chM8QYV2M37xtSZyx4raPAKXc9L3Ns/edit?tab=t.0PMS Email Reminder 30March2026
Step 8
Verification of Approved Proposal | SOLVIVA receives Approved Proposal via Odoo From: Client PMS Email Reminder 30March2026
Steps 11 and 13
Trigger | CLIENT receives Reminder 3 days before PMS Schedule via Email through Odoo From: Aftersales Engr https://docs.google.com/document/d/1zrncD5M-Ky-O2chM8QYV2M37xtSZyx4raPAKXc9L3Ns/edit?tab=t.0PMS Email Reminder 30March2026
CLIENT receives Reminder 1 day before PMS Schedule via Email through Odoo From: Aftersales Engr https://docs.google.com/document/d/1zrncD5M-Ky-O2chM8QYV2M37xtSZyx4raPAKXc9L3Ns/edit?tab=t.0PMS Email Reminder 30March2026
Step 22
Trigger | CLIENT receives Invoice for outstanding balance of 50% and survey via Email through Odoo From: Aftersales Engr https://docs.google.com/document/d/1zrncD5M-Ky-O2chM8QYV2M37xtSZyx4raPAKXc9L3Ns/edit?tab=t.0PMS Email Reminder 30March2026
Step 25
Trigger | CLIENT receives Signed Approved Report via Email through Odoo From: Aftersales Engr https://docs.google.com/document/d/1zrncD5M-Ky-O2chM8QYV2M37xtSZyx4raPAKXc9L3Ns/edit?tab=t.0PMS Email Reminder 30March2026
Channel Reference
Touchpoint | Timing | Primary Channel | Backup Channel
Initial Reminder | Day 1 | Email | Viber
Follow-Up #1 | Day 4 | Email | Viber
Follow-Up #2 | Day 7 | Email + Viber | Phone Call
Escalation | Day 10+ | Internal flag (Odoo) | Supervisor call

## PMS Team
PMS Team | The technical crew (internal or third-party) hired to do the actual work on-site
Role | Clean panels, tighten bolts, and take electrical readings.
Requirement | Must have the required tools and follow the Solviva Checklist.
Aftersales Engr. | Remotely supervise the PMS Team, talk to the client, and sign off on safety
Archelle Natanauan
John Immanuel Faalam
Darill Badidles
CF | Nabeel Paolo Gatchalian
FInance | Christopher Santos
Finance Associate | Kristine Joy Absolir
Marketing | Lili Narvaez
Brand Lead | Patricia Amagsila
CX | Cassandra Milan Mercado

## Checklist for Contractor
|  |  |  | ACTIVITIES | WEIGHT
A. | SOLAR MODULES |  |  |  | 15%
|  |  | 1 | Physical Inspection of all solar modules
|  |  | 2 | Cleaning of modules
B. | MODULE INSTALLATION AND STRUCTURES |  |  |  | 12%
|  |  | 1 | Inspect integrity of all the support structures
|  |  | 2 | Check mounting structures for corrosion
|  |  | 3 | Check module clamps for tightness
|  |  | 4 | Check MS mounting bolts and nuts for tightness
C. | SOLAR ARRAY WIRING AND TERMINATIONS |  |  |  | 20%
|  |  | 1 | Inspection of tightness of connectors
|  |  | 2 | Inspection of connections inside DC Combiner Boxes; check tightness of terminations
|  |  | 3 | Checking all the cables to ensure it is maintained in good condition
D. | SOLAR PV INVERTERS |  |  |  | 18%
|  |  | 1 | Check Inverter display for any errors, warnings
|  |  | 2 | Check tightness of inverter fasteners/brackets
|  |  | 3 | Ensure that the heatsink of the inverter is not covered
|  |  | 4 | Check warning labels and stickers (present and readable)
|  |  | 5 | Clean inverter/controller (if necessary)
|  |  | 6 | Clean the contacts of the DC Isolator Switch/es by cycling the switch to on and off positions TWO times.
E. | AC PANEL BOARDS |  |  |  | 15%
|  |  | 1 | Visual Inspection Body and Safety Labelling
|  |  | 2 | Visual Inspection of all Circuit Breakers
|  |  | 3 | Visual Inspection of SPD/TVSS
|  |  | 4 | Visual Inspection of all cable terminations
|  |  | 5 | Check torque marks and re-tighten if necessary
|  |  | 6 | Clean Panel Board body and devices inside panel board/s
|  |  | 7 | Check operational integrity of Energy Meter
|  |  | 8 | Clean interior of Panel Board (i.e. using vacuum cleaner)
F. | INSPECTION AND TESTING OF OTHER ELECTRICAL ITEMS |  |  |  | 20%
| a. | MONITORING SYSTEM DEVICES AND SENSORS
|  |  | 1 | Visual Inspection of monitoring system - related devices and sensors
|  |  | 2 | Visual Inspection of cable terminations
|  |  | 3 | Clean all Sensors
|  |  | 4 | Check for any sign of damage on all sensors
| b. | INSPECTION OF CABLE TRAYS / CONDUITS
|  |  | 1 | Check integrity of cable tray connections and mountings
|  |  | 2 | Check integrity of cable tray covers
|  |  | 3 | Check for any sign of damage and corrosion
|  |  | 4 | Check grounding jumpers
|  |  |  | TOTAL | 100%

## Equipment, Machine & Tools
A. Electrical Diagnostic Tools
| 1 | Digital Multimeter: For measuring string voltage and current.
| 2 | Clamp Meter: To check active current without disconnecting wires.
| 3 | Insulation Tester (Megger): To verify cable integrity and grounding resistance
| 4 | Infrared (IR) Thermal Camera: To detect "hotspots" in panels and loose breaker connections.
B. Mechanical Maintenance Tools
| 1 | Torque Wrench/Driver: To tighten clamps and terminals to specific manufacturer settings.
| 2 | Insulated Screwdriver Set: 1000V-rated for safe work inside combiner boxes.
| 3 | MC4 Tool Kit: For disconnecting or replacing damaged solar connectors.
| 4 | Cable Management Kit: UV-rated zip ties and clips to fix sagging wires.
C. Professional Cleaning Gear
| 1 | Telescopic Water-Fed Pole: With soft nylon bristles (specifically for solar glass).
| 2 | Low-Pressure Water Source: No high-pressure washers (to avoid damaging panel seals).
D. Mandatory Safety PPE
| 1 | Full Body Harness & Lanyard: Required for all roof-access work.
| 2 | Rubber-Soled Safety Shoes: Non-slip and non-marking to protect the roof and panels.